# COOK ISLANDS VOYAGING SOCIETY (CIVS)

# TIMETABLE OF GOVERNANCE CONSULTATION & PATHWAY TO APPROVAL  AT THE AGM ON 22MARCH 2022

| FRAMEWORK ACTIVITY | DOCUMENTS | PURPOSE | ACTIONING PARTY | DATE | LOCATION L |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GWP UPDATE FOR EB | GOVERNANCE WORKING PARTY | FOR EXECUTIVE BOARD | GWP - JT | WED 2 FEB22 | PORTS AUTHORITY |  |  |
| GWP EB WORKSHOP | GOVERNANCE FRAMEWORK | FOR EXECUTIVE BOARD & MEMBERS | GWP (Caren) | EB OWN FEB TIMETABLE | EB OWN TIMETABLE |
| SOCIETY WORKSHOP | GOVERNANCE FRAMEWORK | FOR ACTIVE VOYAGING CREWS & VOLUNTEERS | EB / GWP | SAT 26 FEB22 (TBC) | SUITABLE SATURDAY TBA |
| CIVS & PARTNERS BREAKFAST MEETING | CIVS GOVERNANCE FRAMEWORK OVERVIEW FOR GOVT & PARTNERS | FOR PM, CI GOV Ministries NGO’s & SOE’s | EB/ GWP | MON 28 FEB22 (TBC) | MINISTRY OF CULTURAL DEVELOPMENT AUDITORIUM 8.00AM – 9.30AM |  |  |
| CIVS AGM WORKSHOP | FRAMEWORK DOCUMENT DETAILED REVIEW | WORKSHOP COMPONENT OF AGM APPROVAL PROCESS | GWP / CIVS -AGM | FRID 4 MAR22 (TBC) | KARIKA MEETING ROOM 2.00PM - 4.00PM |
| MEETING OUR ARIKI’S ARONGA MANA, CSO’S & SPONSORS | CIVS GOVERNANCE FRAMEWORK VIDEO & INFORMAL FUNCTION | HOUSE OF ARIKI, ARONGA MANA, NGO’S, CSO’s SPONSORS & MEMBERS | EB /GWP | FRID 4 MAR22 (TBC) | KARIKA PALACE GROUNDS 4.00PM – 6.00PM |  |  |
| CIVS EXEC BOARD | FRAMEWORK SIGNOFF | EB RESOLUTION TO AGM CIRCULATE AGM NOTICE UPLOAD AGM DOCUMENTS | SEC CIVS EB | MON 7 MAR (TBC) | PORTS AUTHORITY |  |  |
| 2021 AGM | President 2021 Report Audited Financial Statements Adoption of Constitution, Deed of Trust, Governance Handbook | MEMBERS 2021 AGM | EB/CIVS MEMBERS | 22nd MARCH 2022 MOCD AUDITORIUM | MOCD AUDITORIUM 4.30PM – 6.30PM |  |  |

Possibility to merge these 3 activities